## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US01 | Collect research papers from IEEE Xplore – metadata, citations, references | M | None | Y. Navya Teja Sri | 3- Completed
1 | 1 | US02 | Download PDFs/abstracts in bulk from IEEE Xplore | M | US01 | Y. Navya Teja Sri | 3- Completed
1 | 1 | US03 | Parse structured metadata into Excel files (papers.xlsx, citations.xlsx) | M | US02 | Y. Navya Teja Sri | 3- Completed
1 | 1 | US04 | Clean and validate data – duplicates, missing fields, formatting | S | US03 | Y. Navya Teja Sri | 3- Completed
2 | 2 | US05 | Convert Excel files to JSON format using Python in VS Code | M | US03 | Y. Navya Teja Sri | 3- Completed
2 | 2 | US06 | Validate JSON schema consistency across all converted files | M | US05 | Y. Navya Teja Sri | 3- Completed
3 | 3 | US07 | Build knowledge graph with entity extraction, entity relationships and triple relationships stored in Neo4j | M | US06 | Y. Navya Teja Sri | 3- Completed
3 | 3 | US08 | Integrate knowledge graph with RAG pipeline (Hybrid RAG) | M | US07 | Y. Navya Teja Sri | 3- Completed
3 | 3 | US09 | Call LLM API to generate research paper summaries using RAG context | M | US08 | Y. Navya Teja Sri | 3- Completed
3 | 3 | US10 | Evaluate LLM outputs – ROUGE, BLEU, faithfulness metrics | S | US09 | Y. Navya Teja Sri | 3- Completed
3 | 3 | US11 | Evaluate RAG pipeline – precision, recall, context relevance | S | US09 | Y. Navya Teja Sri | 3- Completed
4 | 4 | US12 | Develop UI – summarize query feature | M | US09 | Y. Navya Teja Sri | 3- Completed
4 | 4 | US13 | Add confidence score display for generated summaries | M | US12 | Y. Navya Teja Sri | 3- Completed
4 | 4 | US14 | Implement misleading/out-of-scope question detection | M | US12 | Y. Navya Teja Sri | 3- Completed
4 | 4 | US15 | Final integration testing, UI polish and deployment readiness | S | US12 | Y. Navya Teja Sri | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US01 | 1 | Identify IEEE Xplore search queries for AI/NLP research | 20-Jan-2026 | 22-Jan-2026 | Y. Navya Teja Sri | Data Collection | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US01 | 2 | Collect 50+ papers with metadata from IEEE Xplore | 20-Jan-2026 | 24-Jan-2026 | Y. Navya Teja Sri | Data Collection | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | 3 | Download PDFs and abstracts; organise into folders | 21-Jan-2026 | 24-Jan-2026 | Y. Navya Teja Sri | Data Collection | 3- Completed | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | 4 | Parse metadata into structured Excel files | 23-Jan-2026 | 26-Jan-2026 | Y. Navya Teja Sri | Data Structuring | 3- Completed | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | 5 | Clean data – duplicates, missing fields, normalize keywords | 25-Jan-2026 | 27-Jan-2026 | Y. Navya Teja Sri | Data Validation | 3- Completed | 3 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US05 | 1900-01-05 | Write Python script to convert Excel to JSON | 28-Jan-2026 | 30-Jan-2026 | Y. Navya Teja Sri | Data Transformation | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | 1900-01-06 | Validate JSON output – field mapping and data completeness | 29-Jan-2026 | 31-Jan-2026 | Y. Navya Teja Sri | Data Validation | 3- Completed | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US06 | 1900-01-07 | Schema validation for JSON files using jsonschema library | 30-Jan-2026 | 02-Feb-2026 | Y. Navya Teja Sri | Data Validation | 3- Completed | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US06 | 1900-01-08 | Store validated JSON files and document data pipeline | 01-Feb-2026 | 03-Feb-2026 | Y. Navya Teja Sri | Documentation | 3- Completed | 3 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US07 | 1900-01-09 | Design KG schema – entities (Paper, Author, Topic), relationships | 04-Feb-2026 | 06-Feb-2026 | Y. Navya Teja Sri | KG Design | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US07 | 1900-01-10 | Implement entity extraction from JSON using spaCy NER | 05-Feb-2026 | 09-Feb-2026 | Y. Navya Teja Sri | KG Implementation | 3- Completed | 6 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US07 | 1900-01-11 | Build triple relationships and store knowledge graph in Neo4j using Cypher queries | 07-Feb-2026 | 11-Feb-2026 | Y. Navya Teja Sri | KG Implementation | 3- Completed | 6 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US08 | 1900-01-12 | Implement vector store (FAISS) and embed paper chunks | 09-Feb-2026 | 12-Feb-2026 | Y. Navya Teja Sri | RAG Pipeline | 3- Completed | 6 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US08 | 1900-01-13 | Integrate knowledge graph context with RAG retrieval | 11-Feb-2026 | 14-Feb-2026 | Y. Navya Teja Sri | RAG Pipeline | 3- Completed | 6 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US09 | 1900-01-14 | Integrate LLM API to generate summaries using RAG context | 13-Feb-2026 | 15-Feb-2026 | Y. Navya Teja Sri | LLM Integration | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US10 | 1900-01-15 | Evaluate LLM outputs – ROUGE, BLEU, faithfulness scores | 14-Feb-2026 | 16-Feb-2026 | Y. Navya Teja Sri | Evaluation | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US11 | 1900-01-16 | Evaluate RAG – context relevance, answer relevance, precision | 15-Feb-2026 | 17-Feb-2026 | Y. Navya Teja Sri | Evaluation | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US12 | 18 | Design and build UI layout in Streamlit for summarizer | 18-Feb-2026 | 21-Feb-2026 | Y. Navya Teja Sri | UI Development | 3- Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US12 | 19 | Implement summarize query feature – input, submit, display | 20-Feb-2026 | 23-Feb-2026 | Y. Navya Teja Sri | UI Development | 3- Completed | 5 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US13 | 20 | Add confidence score calculation and display on results page | 22-Feb-2026 | 25-Feb-2026 | Y. Navya Teja Sri | UI Feature | 3- Completed | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US14 | 21 | Implement misleading question detection using classification | 24-Feb-2026 | 27-Feb-2026 | Y. Navya Teja Sri | UI Feature | 3- Completed | 5 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US15 | 22 | End-to-end integration testing of all features | 26-Feb-2026 | 01-Mar-2026 | Y. Navya Teja Sri | Testing | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US15 | 23 | UI polish, bug fixes, documentation and deployment prep | 01-Mar-2026 | 04-Mar-2026 | Y. Navya Teja Sri | Deployment | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 20-Jan-2026 | None | Kick off Sprint 1 – begin data collection from IEEE Xplore
1 | 22-Jan-2026 | IEEE Xplore rate limiting downloads | Switched to IEEE API with request delays
1 | 24-Jan-2026 | Some papers missing abstracts | Flagged and manually filled from IEEE website
1 | 26-Jan-2026 | None | Finalised Excel file structure and validated data
2 | 28-Jan-2026 | None | Begin Python script for Excel to JSON conversion
2 | 30-Jan-2026 | JSON nesting inconsistency for multi-author papers | Flattened author list into array; updated schema
2 | 02-Feb-2026 | None | Completed schema validation and documented pipeline
3 | 04-Feb-2026 | None | Started knowledge graph design and entity schema
3 | 07-Feb-2026 | Neo4j connection issues in local environment | Resolved Neo4j local connection issue by configuring bolt port and adjusting neo4j.conf settings
3 | 10-Feb-2026 | None | Entity extraction working; building triple relationships
3 | 13-Feb-2026 | FAISS index slow on large dataset | Optimised chunk size and batch embedding
3 | 15-Feb-2026 | LLM API rate limit exceeded during testing | Added retry logic with exponential backoff
3 | 17-Feb-2026 | None | RAG + KG integration complete; evaluations running
3 | 09-Feb-2026 | Neo4j Cypher query syntax errors when creating triple relationships | Reviewed Neo4j documentation; corrected Cypher CREATE statements and re-ran ingestion script
3 | 11-Feb-2026 | LLM API (OpenAI GPT-4) connection refused due to missing API key in environment variables | Added API key to .env file and loaded via python-dotenv; connection established successfully
4 | 18-Feb-2026 | None | Started UI design in Streamlit
4 | 21-Feb-2026 | UI layout not responsive on smaller screens | Used Streamlit columns and responsive width settings
4 | 24-Feb-2026 | Confidence score calibration inconsistent | Normalised scores using softmax over retrieval scores
4 | 27-Feb-2026 | Misleading question classifier needs more training data | Used few-shot prompting with LLM as fallback classifier
4 | 03-Mar-2026 | None | Final testing done; preparing project documentation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 20-Jan-2026 | 27-Jan-2026 | Y. Navya Teja Sri | Automate data collection with IEEE API from start | Manual download attempts that caused delays | Structured Excel format for consistent data | Switched to API-based automated downloading
2 | 2 | 28-Jan-2026 | 03-Feb-2026 | Y. Navya Teja Sri | Define JSON schema before writing conversion script | Ad-hoc JSON structure decisions mid-sprint | Python scripting with pandas for data conversion | Defined formal schema and validated against it
3 | 3 | 04-Feb-2026 | 17-Feb-2026 | Y. Navya Teja Sri | Use cloud vector store (Pinecone) instead of local FAISS | Delayed Neo4j setup causing mid-sprint environment issues | Modular RAG pipeline design for easy updates | Configured Neo4j correctly early; triple relationships stored and queried via Cypher
4 | 4 | 18-Feb-2026 | 04-Mar-2026 | Y. Navya Teja Sri | Add unit tests for all UI components from the start | Late-stage UI layout adjustments slowing delivery | Streamlit for rapid UI prototyping | Added responsive layouts and improved confidence display
5
6
7