## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Y. Navya Teja Sri | 22-Jan-2026 | IEEE Xplore API returning incomplete metadata for papers published before 2010 | 1 | Y. Navya Teja Sri | Logical | Updated API query to include legacy DOI lookup and manual fallback | 23-Jan-2026 | Closed | Low priority but resolved to maintain data completeness
2 | Y. Navya Teja Sri | 24-Jan-2026 | Duplicate records in papers.xlsx – same DOI appearing multiple times due to multiple API calls | 1 | Y. Navya Teja Sri | Logical | Added deduplication logic in data cleaning script using DOI as unique key | 25-Jan-2026 | Closed | Affected ~8% of records; all cleaned
3 | Y. Navya Teja Sri | 26-Jan-2026 | Excel file encoding error for special characters in author names (e.g., accented letters) | 1 | Y. Navya Teja Sri | Standards | Changed file encoding to UTF-8-BOM in pandas to_excel export | 26-Jan-2026 | Closed | Impacted 12 records with non-ASCII author names
4 | Y. Navya Teja Sri | 30-Jan-2026 | JSON conversion script failing for papers with more than 5 authors – index out of range error | 2 | Y. Navya Teja Sri | Logical | Refactored author parsing to handle variable-length author lists dynamically | 31-Jan-2026 | Closed | Bug in list indexing; fixed with dynamic loop
5 | Y. Navya Teja Sri | 31-Jan-2026 | JSON output missing 'abstract' field for 6 papers where abstract was stored in separate column | 2 | Y. Navya Teja Sri | Logical | Updated column mapping in conversion script to check alternate column names | 01-Feb-2026 | Closed | Edge case resolved; added field existence check
6 | Y. Navya Teja Sri | 01-Feb-2026 | jsonschema validation throwing false positives for optional fields marked as required in schema | 2 | Y. Navya Teja Sri | Standards | Updated JSON schema to mark optional fields correctly using 'required' array | 02-Feb-2026 | Closed | Schema definition error; corrected definition file
7 | Y. Navya Teja Sri | 07-Feb-2026 | spaCy NER missing entity 'deep learning' as it's a multi-word technical entity | 3 | Y. Navya Teja Sri | Logical | Added custom entity ruler in spaCy pipeline with domain-specific AI/NLP terms | 09-Feb-2026 | Closed | Improved NER recall by ~18% after custom rules added
8 | Y. Navya Teja Sri | 10-Feb-2026 | Neo4j connection failing intermittently – bolt://localhost:7687 refusing connections after system restart | 3 | Y. Navya Teja Sri | Logical | Fixed by updating neo4j.conf to set correct listen address; added auto-restart service config | 11-Feb-2026 | Closed | Session state bug; fixed with serialisation
9 | Y. Navya Teja Sri | 12-Feb-2026 | LLM API (OpenAI GPT-4) connection timeout when generating summaries for papers with >2000 token context | 3 | Y. Navya Teja Sri | Logical | Added connection timeout handling and retry logic; reduced context window to 1800 tokens with sliding window | 13-Feb-2026 | Closed | Dimension was 768 vs 1536 conflict; standardised to 1536
10 | Y. Navya Teja Sri | 14-Feb-2026 | LLM generating summaries exceeding token limit causing truncated output for long papers | 3 | Y. Navya Teja Sri | Logical | Implemented chunked summarisation with map-reduce prompting strategy | 15-Feb-2026 | Closed | Added chunk-level summarisation then final merge
11 | Y. Navya Teja Sri | 16-Feb-2026 | ROUGE score calculation returning NaN for papers with single-sentence abstracts | 3 | Y. Navya Teja Sri | Logical | Added null/length check before ROUGE computation; skip if ref length < 5 tokens | 16-Feb-2026 | Closed | Edge case for very short abstracts
12 | Y. Navya Teja Sri | 21-Feb-2026 | Streamlit UI throwing KeyError when user submits empty query string | 4 | Y. Navya Teja Sri | User Interface | Added input validation and user-facing error message for empty queries | 21-Feb-2026 | Closed | No input guard in original submit handler
13 | Y. Navya Teja Sri | 23-Feb-2026 | Confidence score displaying as raw float (e.g. 0.847321) instead of formatted percentage | 4 | Y. Navya Teja Sri | User Interface | Added formatting to display confidence as rounded percentage (e.g. 84.7%) | 23-Feb-2026 | Closed | UI formatting issue; cosmetic fix applied
14 | Y. Navya Teja Sri | 25-Feb-2026 | Misleading question detector flagging valid queries about 'neural networks' as out-of-scope | 4 | Y. Navya Teja Sri | Logical | Tuned few-shot prompt examples to better distinguish domain-relevant queries | 26-Feb-2026 | Closed | Prompt engineering fix; reduced false positive rate
15 | Y. Navya Teja Sri | 27-Feb-2026 | UI summary results panel not scrollable – long summaries get clipped on screen | 4 | Y. Navya Teja Sri | User Interface | Wrapped results in Streamlit expander and added scrollable text area | 28-Feb-2026 | Closed | Layout issue resolved with Streamlit components
16 | Y. Navya Teja Sri | 01-Mar-2026 | Response time >8 seconds for complex queries – LLM call blocking the UI thread | 4 | Y. Navya Teja Sri | Maintainability | Added asynchronous API call with loading spinner to improve UX | 02-Mar-2026 | Closed | Async wrapper added; avg response time reduced to ~3s
17 | Y. Navya Teja Sri | 09-Feb-2026 | Neo4j Cypher CREATE query failing with SyntaxError when ingesting triple relationships – incorrect property map syntax | 3 | Y. Navya Teja Sri | Logical | Corrected Cypher syntax for property maps; validated all CREATE statements against Neo4j 5.x documentation | 10-Feb-2026 | Closed | Syntax change between Neo4j versions; fixed by aligning to Neo4j 5.x Cypher spec
18 | Y. Navya Teja Sri | 11-Feb-2026 | LLM API (OpenAI GPT-4) connection refused – API key not loaded from environment; requests returning 401 Unauthorized | 3 | Y. Navya Teja Sri | Logical | Added OPENAI_API_KEY to .env file; loaded via python-dotenv at startup; verified with test API call | 11-Feb-2026 | Closed | Environment variable missing from deployment config; resolved and documented in setup guide

## Sheet2
Logical
User Interface
Maintainability
Standards
Others